## Summary
Name of Project | Command Line Finacle Service Management Tool
Project Manager | John Muli
CR Number | CHG0034050
Market | GRP
Business Lead | John Wamai
Down Time Required | N/A
Down Time | N/A
Total Deployment Time | 3 hrs

## Pre-cutover tasks
Planned Time (hh:mm)
Date | Day | Seq | Task Type | Task | Status | Verified by | Owner | Start | End | Dur.
2024-06-20 |  |  | Pre-requisite | Create connection between azure agent and finacle servers DC & DR 10.1.102.135-158 &10.1.38.79-102 | Pending |  | Major /Network Support |  |  | 10mins
|  |  |  | Create AzureFinUser in finacle servers DC & DR 10.1.102.135-158 &10.1.38.79-102 | Pending |  | Amos/ Sysadm |  |  | 10mins
|  |  |  | SSH keys for AzureFinUser to applmgr user in finacle servers | Pending |  | Amos/ Sysadm |  |  | 10mins
|  |  |  | Create Azure service connection for servers DC & DR 10.1.102.135-158 &10.1.38.79-102 | Pending |  | Kevin/ Gatimu |  |  | 2hrs
|  |  |  | Create build and release pipelines | Pending |  | Gatimu |  |  | 2hrs
|  |  |  | Take a back up of the CUST folder in finacle c++ server (Tar file) | Pending |  | Irungu/Sam |  |  | 10mins
|  |  |  | Share production CUST directory | Pending |  | Irungu/Sam |  |  | 5mins

## Main_Cutover
Planned Time (hh:mm)
Date | Day | Seq | Repository | Task Type | Task Details | Status | Downtime Yes/No | Owner | Start | End | Dur.
2024-06-20 | 1 |  | 11_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  | 43_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  | 50_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  | 54_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  | 56_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  | Global_Scripts | Task 1: Configure On-Premises Server - Enable or Disable Servers | i. Go to Pipelines -> Releases in Azure DevOps. ii. Edit the production stages and select the tasks. iii. Enable or disable server tasks as needed. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 2: Generate Pull Requests for Repositories | i. Clone the repository. ii. Pull from the main branch. iii. Copy necessary Finacle files and sh files. iv. Commit and push changes to a new branch. v. Create a pull request to the main branch | pending | No | Gatimu/Kevin |  |  | 10 Mins
|  |  |  | Task 3: Pull Request approvals | At least 3 people to approve the PR. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 4: Monitor CI Pipeline Builds | After the PR, monitor the CI build pipeline: i. Go to Pipelines -> Recent in Azure DevOps. ii. Select the appropriate pipeline and monitor job progress. iii. Check build logs under Checking For Modified Files task. | pending | No | Gatimu/Kevin |  |  | 3 Mins
|  |  |  | Task 5: CD Pipeline Deployment | After CI build, monitor the CD release pipeline: i. Go to Releases -> Pipelines in Azure DevOps. ii. Select the appropriate release and monitor the production stage. iii. Check logs in the Agent job. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 6: Pre-Deployment Approvals | Ensure at least 3 approvers review and approve the release pipeline before deployment. | pending | No | Gatimu/Kevin |  |  | 2 Mins
|  |  |  | Task 7: Deployment Execution | After approvals, the deployment to on-premise servers begins. | pending | No | Gatimu/Kevin |  |  | 5 Mins
|  |  |  | Task 8: Deployment Monitoring (CD) | i. Track CD pipeline progress in Azure Pipelines - Releases. ii. Monitor logs from "Run shell commands on remote machine" section. | pending | No | Gatimu/Kevin |  |  | 5 Mins

## RollBack Procedure
Planned Time (hh:mm)
Date | Date | Seq | Task Type | Task | Status | Downtime Yes/No | Owner | Start (24hrs) | End (24hrs) | Dur. | Comments
| 2024-06-25 | 1 |  | Drop connection from Azure to finacle servers | Pending | NO | Major |  |  | 10mins
|  |  |  | Roll back the Sh scripts in finacle | Pending | NO | Irungu/Sam
|  |  |  | Delete Pipelines in Azure | Pending | NO | Gatimu/Kevin

## Contacts
Name | DO NOT EDIT | DO NOT EDIT | Role | Telephone | Escalation | Escalation Numbers
Samuel Mbogori | 0722630697/0763630697 | Charles Ndirangu | MANAGER | 0722630697/ 0763630697 | John wamai | 0763626695
John Muli |  |  | MANAGER | 0721205409/0763205409 | John wamai | 0763626695
James Irungu |  |  | Officer | 0723677687/0763677687 | John wamai | 0763626695

## Test Plan
Planned Time (hh:mm)
Day | Seq | Task | Status | Verified by | Owner | Start | End | Dur.
2024-04-12 | 1 | Deploy Empty test file | pending |  | Gatimu/James |  |  | 2mins