## Internal Guidance (HIDE) (hidden)
This tab provides internal guidance to WorldRemit staff as how to produce run a Payout API User Acceptance Test. Before the partner is ready to execute UAT, read the below instructions and carry out the required actions.
Follow the below steps in order to conduct the UAT:
1a.) Following the Jmeter Test Transaction Guide to create 30 authorized transactions per payout service in the Integrations (not Staging) Environment.
1b.) All test tnxs must have the recipient name as 'Seán [first name] Alberto-Vázquez [middle name] Mathéo [last name]' - this enables the test that determines whether the partner can display special characters on their platform.
1c.) All test tnxs must have receiver_address_1 as 'Stroud' - this is to ensure, where needed, the partner has mapped the required field as this can be a field that is manually checked when cash pick up transactions are collected
For Cash Pick Up Transactions:
2a.) Paste the transaction numbers into Column E of the Cash Pick Up Test Cash tab, following the rule's specified in Column D regarding the transaction status. Each letter specified in Column D relates to a single transaction reference.
2b.) Paste 10 additional cash pick up test transactions into the grey box immediately below. For partner convenience 8 need to be in authorized status, 1 in hold statis, 1 in cancelled status. These are spare transactions available for the partner to swap into the UAT should a mistake be made/test results not be as expected.
For Other Payout Services:
3a.) - For Mobile Money and Send to a Card Transactions ask for Pre Production and Production MSISDN's (receipient wallet numbers), where relevant. Having got these, ensure that for all transactions that wallet/card mobile number is different from the recipient contact mobile number - this will enable the test that verifies whether the correspondent has the two fields correctly mapped.
3b.) For Bank Transfer Transactions, in order to create Transactions WR need to know the full list of bank name [ie brand], bank codes and branch codes (where applicable). Ask for Pre-production ones (usually a very limited set) and the exhasutive list of Production ones. Use the Pre Production ones in order to then create the test transactions. Both can be added to this document in the Bank Transfer Tests Tab.
3c.) For ALL non cash pickup transactions, having created the 30 transactions per payout service, ensure they are all Authorized . These can then be directly searched for by the partner using Postman, having connected to the WorldRemit pre-production endpoints specified in the Payout API documentation.
Next
4.) Hide this tab
6.) Email this document to the Correspondent test team
7.) Await the completion of this document - both the introduction tab and the respective payout services' tabs must be fully completed by the partner in order to start the verification process. Return the document to the partner if they have not FULLY completed the required fields.
8.) Verify the results per payout service.
View the answers entered in the Introduction tab - do they align with our expectations? If not, raise this to a colleague/ the partner.
Then, go to each of the Test tabs and view the Test Results column. If any of the entries do not contain 'expected result' ask the correspondent why/more details. Otherwise continue with verification:
The 'Verified? [Worldremit Only]' column informs you if the 'expected result' entry can be verified. If the test cannot be verified (eg that a correspondent has carried out a search on a transaction, we need to trust their response.
For those test results that can be verified inspect the transaction events table in Control Money. See if the approropriate action has been executed, along with full details of the expected result.
Select 'Verified' in the 'Verified? [Worldremit Only]' column.
Repeat for each test
Finally, for the test that asks for a screen shot of their User Interface, verify that the correct values exist adjacent to the appropriate parameter. Challenge anything that doesn't appear to relate, or if there are missing values thatmay be mandatory (not all parameters are) - eg beneficiary name. You can use the Payout API documentation or the Example tabs adjacent to the Send to a Card Test Tab to see examples of what parameters & values should exist.
9.) If you can verify that all tests results match with the expected results, UAT is complete.
10.) Sign the delcaration testifying UAT has been verified and completed
11.) Save this document in the respective Correspondent folder in Operations shared drive - \\wrlonfile00\Departments\OPERATIONS\01 Correspondents\Correspondents
12.) Commence live testing

## Introduction
Welcome to the WorldRemit PayOut API v2 User Acceptance Test (UAT) document. The aim of this document is to act as a test framework to assess whether the integration is fit to move into the Production environment as well as to track and record the progress such assessment. This UAT focuses on whether the expected behavior takes place while a transaction is processed. Correspondent partners of WorldRemit MUST complete this UAT document as guided, or the integration cannot progress to live. As a preparation for the UATs, please answer the following questions:
Questions |  | Answer
List which payout services (cash pickup, bank transfer, mobile money, send to a card) have you integrated for (ensure that your answers are aligned to your respective business departent. No partner integrates all services contained in the Payout API document.
Has the Payout API document been exhaustively checked for which API methods are relevant to the services that are in scope for the integration? Note: Some methods are not relevant to some services.
Has all development been completed?
List here ALL of the Response Codes your organisation plan to use in the live system (not all are relevant for each service/your organisation), breaking it down by payout service. Check the Response Codes tab or the API document for full list of response codes.
For Cash Pick-up (CPU) transactions: The test transaction references to use are specified in Column F of the Cash Tests tab. For all other payout services: To locate Bank Transfer (BT) or Mobile Money (MM) test transactions directly, search and retrieve them via the PayOut API methods - see the PayOut API documentation as to how to execute this. For ALL services: Go to relevant 'Tests' tab(s) and complete the tests. Carry out the tests with the available transactions, WorldRemit will create those for you prior to testing wherever applicable (some scenarios requires interaction between you and the WorldRemit technical team - details will be provided while you will be reviewing this document with the WorldRemit technical team prior to the UATs). Make sure you INPUT THE RESULT in the 'Test Result' column (if you obtained an expected result, then a simply 'OK' would suffice) and change the background color of the cell that is relevant to the test case step - see the Color-coding information below. WorldRemit will then verify the input result alongside what our system informs us with regards to the status of a transaction. Should the two results match and your teams are satisfied that expected behavior has taken place, this means that the scenario has been successfully completed. Repeat this for all the test scenarios that are in scope. If certain test scenarios require specific data to be tested (e.g. a bank account or mobile number that is going to be accepted/rejected on your side), then provide this information in the Comment column for steps where 'WorldRemit creates a pending transaction'. If you have any questions, contact WorldRemit for any clarification.
Color-coding
As this document also aims to track the testing progress, color-coding has been introduced to help grasp the overall progress / status more easily
Color | Meaning | Action required
grey | Out of scope | None - the scenario is not applicable in your case
blue (light or dark) | To be tested | You should carry out the test case as per defined steps
orange | To be verified | WorldRemit to verify the scenario/step
red | Error occurred while testing | You need to fix the problem encountered while testing and then mark the scenario yellow
yellow | Test transaction required | WorldRemit to create a new test transaction, provide its ID/reference and mark the scenario blue
green | Tested & verified successfully (i.e. expected results received) | None - the scenario has been completed
FOR WORLDREMIT STAFF ONLY | Name | Date
I hereby confirm that I have verified the partner's test results; live tests can now commence

## Response Codes
Response code | Response message | Resulting state | Description
0001 | Bank account number invalid | Failed | Bank account number invalid
0002 | Recipient contact details invalid | Failed | Recipient telephone number or email address in invalid
0003 | Bank account type not supported | Failed | Bank account type invalid
0004 | Mobile Account number invalid | Failed | Designated Mobile Money Wallet invalid
0005 | Bank code invalid | Failed | Designated bank code invalid
0006 | Invalid Bank Branch Code | Failed | Designated branch code invalid
0007 | Account dormant or inactive | Failed | Designated account is not valid because it is dormant or inactive
0008 | Account held in different Currency Type | Failed | The remittance payout currency is different from the currency type of the account
0009 | Missing or incomplete Recipient Reference | Failed | A reference or change to the reference is required
0010 | Recipient account name mismatch | Failed | The account holder name and the name specified by the sender is different
0011 | Max amount per transaction for Recipient exceeded | Failed | A transaction value limit has been exceeded
0012 | Max amount per 24 hours for Recipient exceeded | Failed | A 1 day transaction value limit has been exceeded
0013 | Max amount per 30 days for Recipient exceeded | Failed | A 30 day transaction value limit has been exceeded
0014 | Max number of transactions per 24 hours for Recipient exceeded | Failed | A 1 day transaction volume limit has been exceeded
0015 | Max number of transactions per 30 days for Recipient exceeded | Failed | A 30 day transaction volume limit has been exceeded
0016 | Max amount per transaction for Sender exceeded | Failed | A sender-specific transaction value limit has been exceeded
0017 | Max amount per 24 hours for Sender exceeded | Failed | A sender-specific transaction value limit has been exceeded in a 1 day period
0018 | Max amount per 30 days for Sender exceeded | Failed | A sender-specific transaction value limit has been exceeded in a 30 day period
0019 | Max number of transactions per 24 hours for Sender exceeded | Failed | A sender-specific transaction volume limit has been exceeded in a 1 day period
0020 | Max number of transactions per 30 days for Sender exceeded | Failed | A sender-specific transaction volume limit has been exceeded in a 30 day period
0021 | Below minimum amount per transaction threshold | Failed | The value of the transaction is below the required amount
0022 | Max wallet balance exceeded | Failed | The recipient’s wallet would exceed the store of value were the payment be credited
0023 | Intended recipient did not register an account | Failed | The recipient did not register for a mobile money wallet in order to receive the funds
0024 | KYC failed | Failed | Recipient KYC checks did not pass required level
0025 | Intended recipient did not register for card | Failed | The recipient did not register for a card product in order to receive the funds
0026 | Invalid card number | Failed | The specified card number is not valid
0027 | Invalid MSISDN | Failed | The specified mobile telephone number is not valid
0028 | Funds not collected | Failed | Recipient did not collect the funds (no reg required)
0029 | Recipient ID mismatch | Failed | The recipient’s ID did not match the details specified in the transaction
0030 | Insufficient Funds | Failed | There is not sufficient wholesale funds to enable the recipient to be credited
0031 | KYC in Progress (Not used/applicable for reject method – only use for Update Status description method) | Acknowledged | Acts as an update to WorldRemit that the recipient needs first to register/be KYCd before funds can be credited
0032 | Cancellation Requested by WorldRemit/Sender | Cancelled | WR has requested the transaction to be not paid and rejected
0033 | Downstream connection/system issue means transaction not yet created with end institution (Not used/applicable for reject method – only use for Update Status description method) | Failed | There is a problem between your organisation and the end institution who will ultimately credit the beneficiary. This is used to update WR/the sender (not to reject the transaction).
0034 | End institution due to provide status update (Not used/applicable for reject method – only use for Update Status description method) | Failed | The end institution has received the transaction but has yet to indicate whether it has been successfully paid. This is used to update WR/the sender (not to reject the transaction).
0035 | Transaction progress update | Acknowledged | Generic Transaction progress update. Additional information to be provided in the "comment" field of the response.
0036 | Downstream issue, status to be confirmed by Correspondent | Acknowledged | A callback is expected from the correspondent to update the state of the transaction.
0040 | Generic error (correspondent can provide more details if they are available) | Failed | There was an error of a kind that cannot be attributed to any other existing error type/code.
0041 | Recipient name on restricted list | Failed | The recipient name is on a restricted list (Blacklisted).
0042 | Sender name on restricted list | Failed | The sender name is on a restricted list (Blacklisted).
0050 | Beneficiary not getting OTP due to network issues | Awaiting | When a correspondent wants to unlock a locked transaction to re-generate and resend the OTP
0051 | Recipient account name mismatch | Awaiting | The account holder name and the name specified by the sender is different

## Bank Tests
| USER ACCEPTANCE TESTS |  | ALL Operational and non technical processes in place in the live environment will be implemented/tested here as part of the UAT to ensure these UAT tests reflect the processes involved for real transactions
BANK TRANSFER
| Test case name | Test case step | Step description | Method under test | Comment | WR ONLY (txn references) | Expected response code / behavior |  | Test Results | Verified? [WorldRemit Only] | Notes
1 | Heartbeat test | 1 | Verify the hearbeat | Heartbeat (webhook) | This tests the connectivity and also ensure the credentials provided are working as expected |  | 200 OK | Transaction details have been returned
2 | Happy case | 2a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid bank account details: [TODO]
|  | 2b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 2c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 2d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 2e | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid |  | 200 OK | The transaction has been marked as paid
3 | Error case – invalid bank account | 3a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Invalid bank account details: [TODO]
|  | 3b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 3c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 3d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 3e | Mark the locked transaction as Failed with Response code "0001" ("Bank account number invalid") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
4 | Error case – name mismatch | 4a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid bank account details (name to be modified): [TODO] | [5 empty] | Recipient name won't be checked at the moment
|  | 4b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 4c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 4d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 4e | Mark the locked transaction as Failed with Response code "0010" ("Recipient account name mismatch") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
5 | Error case – account type is not supported | 5a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Bank account details of unsupported type: [TODO] | [5 empty] | No account type check
|  | 5b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 5c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 5d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 5e | Mark the locked transaction as Failed with Response code "0003" ("Bank account type not supported") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
6 | Error case – invalid bank code | 6a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Invalid bank code account details: [TODO] | [5 empty] | No bank code check
|  | 6b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 6c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 6d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 6e | Mark the locked transaction as Failed with Response code "0005" ("Bank code invalid") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
7 | Error case – account is not active | 7a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Inactive/dormant bank account details: [TODO] | [5 empty] | No account inactive validation
|  | 7b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 7c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 7d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 7e | Mark the locked transaction as Failed with Response code "0007" ("Account dormant or inactive") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
8 | Error case – invalid currency | 8a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid bank account details w/unsupported currency: [TODO]
|  | 8b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 8c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 8d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 8e | Mark the locked transaction as Failed with Response code "0008" ("Account held in different currency type") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
9 | Error case – transaction limit | 9a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: 5000 USD (test 50)
|  | 9b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 9c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 9d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 9e | Mark the locked transaction as Failed with Response code "0011" ("Max amount per transaction for recipient exceeded") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
10 | Error case – daily limit | 10a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: 10k (100)
|  | 10b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 10c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 10d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 10e | Mark the locked transaction as Failed with Response code "0012" ("Max amount per 24 hours for recipient exceeded") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
11 | Error case – monthly limit | 11a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No montly limits
|  | 11b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 11c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 11d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 11e | Mark the locked transaction as Failed with Response code "0013" ("Max amount per 30 days for recipient exceeded") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
12 | Error case – daily count limit | 12a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No daily count limits
|  | 12b | Call Cancellation Lock Note: this step should be skipped if the cancellation auto-lock has been agreed with WorldRemit technical team, i.e. cancellation requests are autmoatically locked when Transaction Cancellation Awaiting is called (previous step) | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 12c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 12d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 12e | Mark the locked transaction as Failed with Response code "0014" ("Max txns per 24 hrs for recipient exceeded") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
13 | Error case – minimum amount | 13a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO]
|  | 13b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 13c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 13d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 13e | Mark the locked transaction as Failed with Response code "0021" ("Below minimum amount per transaction threshold") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
14 | Happy case – KYC delayed | 14a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | No KYC check
|  | 14b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 14c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 14d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 14e | Mark the locked transaction as Acknowledged with Response code "0031" ("KYC in progress") | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
15 | Error case – KYC failed | 15a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | No KYC check
|  | 15b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 15c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 15d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 15e | Mark the locked transaction as Failed with Response code "0024" ("KYC failed") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
16 | Beneficiary update + iteration (Error case + happy case) | 16a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Invalid bank account details: [TODO]
|  | 16b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 16c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 16d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 16e | Mark the locked transaction as Failed with Response code "0001" ("Bank account number invalid") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
|  | 16f | WorldRemit changes recipient details and resends the transaction with an iteration (e.g 1234567890001) WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid bank account details: [TODO] | to be provided only after the previous step
|  | 16g | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 16h | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 16i | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 16j | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
17 | Error case – downstream issue | 17a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 17b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 17c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 17d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 17e | Mark the locked transaction as Failed with Response code "0033" ("Transaction could not be paid due to technical issue") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
18 | Error case – recipient name on restricted list | 18a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Recipient name should be in the correspondent's restricted list | [5 empty] | Temporary the test case is on review by Equity
|  | 18b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 18c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 18d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 18e | Mark the locked transaction as Failed with Response code "0041" ("Recipient name on restricted list") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
19 | Error case – sender name on restricted list | 19a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Sender name should be in the correspondent's restricted list | [5 empty] | Temporary the test case is on review by Equity
|  | 19b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 19c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 19d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 19e | Mark the locked transaction as Failed with Response code "0042" ("Sender name on restricted list") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
Transaction Status Request
20 | Transaction status request – manual | 20a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 20b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 20c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 20d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 20e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 20f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 20g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 20h | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
21 | Transaction status request – automatic | 21a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 21b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 21c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 21d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 21e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 21f | WorldRemit automatically requests a Status Request after 20 minutes If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 21g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 21h | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
22 | Transaction status – transaction not found | 22a | WorldRemit requests a Status Request for a transaction which has not been processed by Partner. If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 22b | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Transaction details have been returned
|  | 22c | Mark the locked transaction as Failed with Response code "0040" ("Transaction not found") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
23 | Transaction status leading to failure | 23a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 23b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 23c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 23d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 23e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 23f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 23g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 23h | Mark the locked transaction as Failed with Response code "0033" "Transaction could not be paid due to Technical issue" or any other error | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
24 | Transaction status – multiple requests | 24a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 24b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 24c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 24d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 24e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response 1/2 | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 24f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 24g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 24h | Mark the locked transaction as Acknowledged with Response code the same in Step 22e | Transaction Set Response 2/2 | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 24i | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 24j | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request status details have been returned
|  | 24k | Mark the locked transaction as Paid | Transaction Paid | This tests the partner can mark a transaction as paid |  | 200 OK | Transaction marked as paid.
Transaction Cancellation Request
25 | Cancellation – happy case | 25a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | Cancellation not supported
|  | 25b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 25c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 25d | WorldRemit creates a pending cancellation request for the payment transaction above: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a cancellation is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting cancellations.
|  | 25e | Call Cancellation Awaiting | Cancellation Awaiting | This tests the partners can pick up transaction cancellation requests |  | 200 OK | Cancellation details have been returned
|  | 25f | Call Cancellation Lock Note: this step should be skipped if the cancellation auto-lock has been agreed with WorldRemit technical team, i.e. cancellation requests are autmoatically locked when Transaction Cancellation Awaiting is called (previous step) | Cancellation Lock | This tests if the partner can successfully lock a cancellation request |  | 200 OK | Cancellation request has been locked
|  | 25g | Call Cancellation Set Response (success: True) | Cancellation Set Response | This tests the partner can mark a transaction cancellation as successfully completed |  | 200 OK | The transaction has been marked as cancelled and the cancellation request as completed
|  | 25h | Mark the locked payment transaction as Cancelled with Response code "0032" "Cancellation Requested by WorldRemit/Sender" | Transaction Set Response | This tests your system allows you to mark a transaction as cancelled |  | 200 OK | The transaction defined in Step 25a is not completed
26 | Cancellation – cancel impossible | 26a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | Cancellation not supported
|  | 26b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 26c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 26d | WorldRemit creates a pending cancellation request: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a cancellation is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting cancellations.
|  | 26e | Call Transaction Cancellation Awaiting | Cancellation Awaiting | This tests the partners can pick up transaction cancellation requests |  | 200 OK | Cancellation details have been returned
|  | 26f | Call Cancellation Lock Note: this step should be skipped if the cancellation auto-lock has been agreed with WorldRemit technical team, i.e. cancellation requests are autmoatically locked when Transaction Cancellation Awaiting is called (previous step) | Cancellation Lock | This tests if the partner can successfully lock a cancellation request |  | 200 OK | Cancellation request has been locked
|  | 26g | Call Cancellation Set Response (success: False, responsecode: 0810, responsemessage and comment set appropriately, e.g. "Unable to cancel", "Transaction already paid") | Cancellation Set Response | This tests the partner can inform WR that a transaction could not be cancelled |  | 200 OK | Cancellation request has been marked as completed
|  | 26h | Complete the processing of the payment transaction | Transaction Set Paid / Response | This tests if the payment transaction can be completed normally dispite a request to be cancelled |  | 200 OK | The transaction defined in Step 26a has been completed

## Mobile Tests
| USER ACCEPTANCE TESTS |  | ALL Operational and non technical processes in place in the live environment will be implemented/tested here as part of the UAT to ensure these UAT tests reflect the processes involved for real transactions
MOBILE
| Test case name | Test case step | Step description | Method under test | Comment | WR ONLY (txn references) | Expected response code / behavior |  | Test Results | Verified? [WorldRemit Only] | Notes
1 | Heartbeat test | 1 | Verify the hearbeat | Heartbeat (webhook) | This tests the connectivity and also ensure the credentials provided are working as expected |  | 200 OK | Transaction details have been returned
2 | Happy case | 2a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid mobile number: [TODO]
|  | 2b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 2c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 2d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 2e | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | The transaction has been marked as paid
3 | Error case – invalid account | 3a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Invalid mobile number: [TODO]
|  | 3b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 3c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 3d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 3e | Mark the locked transaction as Failed with Response code "0004" ("Mobile account number invalid") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
4 | Error case – transaction limit | 4a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO]
|  | 4b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 4c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 4d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 4e | Mark the locked transaction as Failed with Response code "0011" ("Max amount per transaction for recipient exceeded") | Transaction Set Response | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
5 | Error case – daily limit | 5a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | Daily limit possibility on review by Equity
|  | 5b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 5c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 5d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 5e | Mark the locked transaction as Failed with Response code "0012" ("Max amount per 24 hours for recipient exceeded") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
6 | Error case – monthly limit | 6a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No montly limits
|  | 6b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 6c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 6d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 6e | Mark the locked transaction as Failed with Response code "0013" ("Max amount per 30 days for recipient exceeded") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
7 | Error case – daily count limit | 7a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No daily count limits
|  | 7b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 7c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 7d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 7e | Mark the locked transaction as Failed with Response code "0014" ("Max txns per 24 hrs for recipient exceeded") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
8 | Error case – monthly count limit | 8a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No monthly count limits
|  | 8b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 8c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 8d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 8e | Mark the locked transaction as Failed with Response code "0014" ("Max txns per 24 hrs for recipient exceeded") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
9 | Error case – minimum amount | 9a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO]
|  | 9b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 9c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 9d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 9e | Mark the locked transaction as Failed with Response code "0021" ("Below minimum amount per transaction threshold") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
10 | Error case – maximum balance | 10a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Limit: [TODO] | [5 empty] | No balance validation
|  | 10b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 10c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 10d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 10e | Mark the locked transaction as Failed with Response code "0022" ("Max wallet balance exceeded") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
11 | Error case – account not registered | 11a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  | Valid but not registered mobile number: [TODO] | [5 empty] | No account registration validation
|  | 11b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 11c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 11d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 11e | Mark the locked transaction as Failed with Response code "0023" ("Intended recipient did not register an account") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
12 | Happy case – KYC delay | 12a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | No KYC check
|  | 12b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 12c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 12d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 12e | Mark the locked transaction as Acknowledged with Response code "0031" ("KYC in progress") | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
13 | Error case – KYC failed | 13a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | No KYC check
|  | 13b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 13c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 13d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 13e | Mark the locked transaction as Failed with Response code "0024" ("KYC failed") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
14 | Error case – downstream issue | 14a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 14b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 14c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 14d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 14e | Mark the locked transaction as Failed with Response code "0033" ("Transaction could not be paid due to technical issue") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
15 | Beneficiary update + iteration (Error case + happy case) | 15a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 15b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 15c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 15d | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 15e | Mark the locked transaction as Failed with Response code "0004" ("Mobile account number invalid") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
|  | 15f | WorldRemit changes recipient details and resends the transaction with an iteration (e.g 1234567890001) WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. |  |  | to be provided only after the previous step
|  | 15g | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 15h | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are autmoatically locked when Transaction Awaiting is called (previous step) | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 15i | Read the locked transaction | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 15j | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | The transaction has been marked as paid
Transaction Status Request
16 | Transaction status request – manual | 16a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 16b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 16c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 16d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 16e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 16f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 16g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 16h | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
17 | Transaction status request – automatic | 17a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 17b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 17c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 17d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 17e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 17f | WorldRemit automatically requests a Status Request after 20 minutes If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 17g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 17h | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
18 | Transaction status – transaction not found | 18a | WorldRemit requests a Status Request for a transaction which has not been processed by Partner. If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 18b | Call transaction status awaiting | Transaction Awaiting | This tests the partners can pick up status requests |  | 200 OK | Transaction details have been returned
|  | 18c | Mark the locked transaction as Failed with Response code "0040" ("Transaction not found") | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
19 | Transaction status leading to failure | 19a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 19b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 19c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 19d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 19e | Mark the locked transaction as Acknowledged with Response either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 19f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 19g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 19h | Mark the locked transaction as Failed with Response code "0033" Transaction could not be paid due to Technical issue | Transaction Set Failed | This tests your system allows you to fail a transaction with the relevant response code and message |  | 200 OK | The transaction has been marked as failed
20 | Transaction status – multiple requests | 20a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions.
|  | 20b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 20c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 20d | Read the locked transaction - optional in this test scenario | Transaction Read | This tests if details of a locked transaction can be read by your system |  | 200 OK | Transaction details have been returned
|  | 20e | Mark the locked transaction as Acknowledged with Response code either "0036" ("Downstream issue. Status to be confirmed") or "0035" ("Transaction available with downstream partner" or similar) | Transaction Set Response 1/2 | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 20f | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 20g | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request details have been returned
|  | 20h | Mark the locked transaction as Acknowledged with Response code the same in Step 20e | Transaction Set Response 2/2 | This tests your system allows you to signal a transaction as delayed without failing it |  | 200 OK | The transaction has been marked as acknowledged
|  | 20i | WorldRemit requests a Status Request If webhooks are implemented, WorldRemit will notify Status Request Pending. If webhooks are not implemented, the partner should poll at regular intervals for Status Request
|  | 20j | Call transaction status awaiting | Transaction Status Awaiting | This tests the partners can pick up status requests |  | 200 OK | Status request status details have been returned
|  | 20k | Mark the locked transaction as Paid | Transaction Paid | This tests if the partner can mark a transaction as paid. |  | 200 OK | Transaction marked as paid.
Transaction Cancellation Request
21 | Cancellation – happy case | 21a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | Cancellation not supported
|  | 21b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 21c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 21d | WorldRemit creates a pending cancellation request for the payment transaction above: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a cancellation is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting cancellations.
|  | 21e | Call Cancellation Awaiting | Cancellation Awaiting | This tests the partners can pick up transaction cancellation requests |  | 200 OK | Cancellation details have been returned
|  | 21f | Call Cancellation Lock Note: this step should be skipped if the cancellation auto-lock has been agreed with WorldRemit technical team, i.e. cancellation requests are autmoatically locked when Transaction Cancellation Awaiting is called (previous step) | Cancellation Lock | This tests if the partner can successfully lock a cancellation request |  | 200 OK | Cancellation request has been locked
|  | 21g | Call Cancellation Set Response (success: True) | Cancellation Set Response | This tests the partner can mark a transaction cancellation as successfully completed |  | 200 OK | The transaction has been marked as cancelled and the cancellation request as completed
|  | 21h | Mark the locked payment transaction as Cancelled with Response code "0032" "Cancellation Requested by WorldRemit/Sender" | Transaction Set Response | This tests your system allows you to mark a transaction as cancelled |  | 200 OK | The transaction defined in Step 21a is not completed
22 | Cancellation – cancel impossible | 22a | WorldRemit creates a pending transaction: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a transaction is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting transactions. | [7 empty] | Cancellation not supported
|  | 22b | Get a list of IDs of all the pending transactions | Transaction Awaiting | This tests the partner's use of the webhook and ability to pick up transactions |  | 200 OK | Transaction details have been returned
|  | 22c | Lock the transaction defined for this scenario (see Trx reference in Column G) Note: this step should be skipped if the transaction auto-lock has been agreed with WorldRemit technical team, i.e. transactions are automatically locked when Transaction Awaiting is called (previous step); optionally, the transaction can be also Read and/or Acknowledged before proceeding to the next step. | Transaction Lock | This tests if the partner can successfully lock a transaction |  | 200 OK | The transaction has been locked
|  | 22d | WorldRemit creates a pending cancellation request: If webhooks are implemented, WorldRemit will invoke the webhook to notify you that a cancellation is pending. If webhooks are not implemented, the partner should poll at regular intervals for awaiting cancellations.
|  | 22e | Call Transaction Cancellation Awaiting | Cancellation Awaiting | This tests the partners can pick up transaction cancellation requests |  | 200 OK | Cancellation details have been returned
|  | 22f | Call Cancellation Lock Note: this step should be skipped if the cancellation auto-lock has been agreed with WorldRemit technical team, i.e. cancellation requests are autmoatically locked when Transaction Cancellation Awaiting is called (previous step) | Cancellation Lock | This tests if the partner can successfully lock a cancellation request |  | 200 OK | Cancellation request has been locked
|  | 22g | Call Cancellation Set Response (success: False, responsecode: 0810, responsemessage and comment set appropriately, e.g. "Unable to cancel", "Transaction already paid") | Cancellation Set Response | This tests the partner can inform WR that a transaction could not be cancelled |  | 200 OK | Cancellation request has been marked as completed
|  | 22h | Complete the processing of the payment transaction | Transaction Set Paid / Response | This tests if the payment transaction can be completed normally dispite a request to be cancelled |  | 200 OK | The transaction defined in Step 22a has been completed