## Sheet1
# | Issue | Action | To Do | Status
1 | Value date issue | Commented txmttcietxndp015 scrip on MTT.PartTranDetails.ValueDate = BANCS.STDIN.BODDate | To be deployed in preprod | Closed
2 | Mpesa/ Airtel Auton Reversal | Provided API to MFS team | MFS to action from their side | Testing in Progress
3 | Airtel Money Transactions Failing | Enabled Airtel B2C GL to collect charges | Finacle prod to deploy changes In prod - IM266888 | Closed
4 | Faiba Money Transactions | 1. change faiba revenue gl from 0006500104028 Mica Revenue to 0006500105208 Faiba Money Revenue 2. Add bacid ECOCOMM to 0006500105208 Faiba Money Revenue 3. Replicate XXX6500105208 to all sols in 54 4. Rename Eco Revenue GL 6000650014594 in Finacle 99 sol 6000 to Faiba Money Revenue 5. Add bacid ECOCOMM to 6000650014594 | Finacle prod to deploy changes In prod - IM266887 | Closed
5 | Faiba Money Transactions | Change Faiba money script to change the bacid of the faiba revenue from ECOREV to ECOCOMM | Changes to be deployed in preprod | Closed
6 | 10 Mins Same Transactions challenge for mKey | 1. Exempt the below GLs in 54 from the 10 mins waiting period for the transactions of the same amount. 0001400305024 Mpesa B2c 0001400305207 Airtel B2c 0003001605048 - FINSERVE INTERCOMPANY PAYABLE-FINTECH 0001100105046 M-KEY OUTGOING SETTLEMENT GL for RTGS 0001100104442 PesaLink SETTLEMENT GL | Signing of change request in progress | Closed
7 | RTGS narrations | RTGS narrations |  | Open
8 | Billers Narrations | Requirement sent to MFS to include the Biller name on the narration. | Discussion ongoing | Open
9 | Account Creation BOD date | send BOD date in account open request. This will lead to adding of an extra BOD tag on the transaction API | To discuss with Manju | Open
MFS different Error Codes
Paul Ndugu wallet ID issue
Airtime Gl excemption issue
RTGS pesalink narration issue

## Release notes 11
1 | Opening Balance for the Day
2 | MFS SOUTH SUDAN CREATION