## Sheet1
Application | Tier | Has DR? | Subsidiary | App Description | Direct Customer Service | Interdependency | Dependemcies | Schedule (H1/H2) | Date Failed Over | Failed Over? | OWNER | BUSINESS OWNER | QUARTER | Month | Date | Time
Autobranch | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Card Production | YES | NO |  |  |  |  | Annet Ayuko |  | Q2 | May | 16/05/2026 | 5.00 PM
Biometrics | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Authentication | NO | NO | [6 empty] | Q4
Cashcloud/Equity Online for Business (MCR) |  | YES | Kenya,Uganda,Rwanda,DRC,South Sudan |  | YES | [7 empty] | Q1 | Feb | 2026-08-02 | 10.00PM
Clear vision | T2 | YES | Kenya | Investment banking services | NO | NO |  |  |  |  | Victor Kiplagat |  | Q2 | May | 15/05/2026 | 5.00PM
Crowdstrike | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Cybersecurity | NO | NO | [6 empty] | Q3
DFS |  | YES | Finserve,KENYA | Digital Financial system |  | NO | [6 empty] | Q1 | Feb/Mar
Diaspora Portal | T2 | NO | Kenya | PayPal remittance | YES | NO | [6 empty] | N/A
Eazzybiz - KE, UG, RW, DRC, SS | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Corporate Ebanking | YES | NO | [6 empty] | Awaiting confirmation
Cashcloud/Equity Online for Business TZ | T2 | YES | Tanzania | Corporate Ebanking | YES | NO | [6 empty] | Q2
Efront | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Finacle Front End Services | YES | NO |  |  |  |  | Marion Kinyanjui |  | Q2 | April | 23/04/2026 | 10.00 P.M
Equity Direct (KE, UG, RW, TZ) | T1 | YES | Kenya,Uganda,Rwanda,Tanzania | Cross border funds transfer | YES | NO
ERP | T2 | NO | Kenya,Uganda,Rwanda,DRC,South Sudan | Employee detail/Payments/Reporting | NO | NO | [6 empty] | N/A
Finacle Core - KE,SS | T1 | YES | Kenya,South Sudan | Core Banking | YES | YES | [6 empty] | Q3
Finacle Core - UG | T1 | YES | Uganda | Core Banking | YES | YES | [6 empty] | Q3
Finacle Core - RW | T1 | YES | Rwanda | Core Banking | YES | [7 empty] | Q3
Finacle Core - DRC | T1 | YES | DRC | Core Banking | YES | [7 empty] | Q3
Finacle Core TZ | T1 | YES | Tanzania | Core Banking | YES | YES |  |  |  |  | Raymond |  | Q1 | Mar | 15/03/2026 | 08.00PM
Finacle Treasury - KE, UG, RW, DRC, SS | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Treasury and trading services | YES | NO | [6 empty] | Q3
Finacle Treasury - TZ | T1 | YES | Tanzania | Treasury and trading services | YES | NO |  |  |  |  | Raymond |  | Q1 | Mar | 15/03/2026 | 08.00PM
Finastra | [12 empty] | Q4
GAG - Transfer to wallets (B2C & C2B) | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Remittance | NO | YES |  |  |  |  | Millicent Ochola |  | Q2 | June | 2026-07-05 | 12.00PM
Imperva | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Cybersecurity | NO | NO | [6 empty] | Q3
Johari | [10 empty] | Peter Mukavane |  | Q2
K Printer | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | SWIFT | YES | NO |  |  |  |  | Richard Ndungu |  | Q2 | June | 13/06/2026 | 8.00 PM
MFA Duo | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Access Management | NO | NO | [6 empty] | Q3
MFS - app, stk, agency merchants | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | app, stk, agency merchants | YES | NO |  |  |  |  | John Karanja |  | Q1 | Feb | 21/02/2026 | 12.00AM
Newgen | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Loan Origination | NO | NO |  |  |  |  | Timothy/Titto |  | Q1 | Mar | 19/03/2026 | 08.00P.M
ORS | T2 | YES | Kenya | Remittance | YES | NO | [6 empty] | Q3
PCS Custody | T2 | YES | Kenya | Custody services | NO | NO | [6 empty] | Q3
SIEM | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Cybersecurity | NO | NO | [6 empty] | Q4
SMSC | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | SMS | NO | YES | [6 empty] | Q2
SMC | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan,Tanzania | SMS Router | NO | YES |  |  |  |  | Moses Muriuki |  | Q1 | Feb | 15/02/2026 | 10.00 P.M
SOA | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Integration of services | NO | YES |  |  |  |  | Faith Githaiga | Keziah Waithaka/Eric Rutere | Q2 | June | 14/06/2026 | 10.00 P.M
STK Services (MGW, OTA, MFS STK) | T1 | YES | Kenya | Equitel | YES | NO |  |  |  |  | Moses Muriuki |  | Q1 | Feb | 15/02/2026 | 10.00 PM
Telephony | T2 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | BULK SMS | NO | NO | [6 empty] | Q4
Turnquest | T1 | YES | Kenya | Insurance | NO | NO |  |  |  |  | Titus Kiio/Benedit Suma |  | Q2 | May | 22/05/2026 | 8.00 PM
Unit master | T2 | YES | Kenya | Investment banking services (Asset Management)-Unit trust | NO | NO |  |  |  |  | Victor Kiplagat |  | Q2 | May | 22/05/2026 | 8.00 PM
VPH KE & UG | T1 | YES | Kenya,Uganda | Clearing System | YES | NO | [6 empty] | Q3
VPH RW | T1 | YES | Rwanda | Clearing System | YES | NO | [6 empty] | Q3
VPH TZ | T1 | YES | Tanzania | Clearing System | YES | NO |  |  |  |  | Marrisiano |  | Q1 | Mar | 14/03/2026 | 4.00 AM
VPN Express Route | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | VPN | NO | NO |  |  |  |  | Victor Muluve |  | Q1 | Feb | 22/02/2026 | 10.00P.M
Way4 | T1 | YES | Kenya,Uganda,Rwanda,DRC,South Sudan | Payments - Cards | YES | YES | [6 empty] | Q2 | June | 21/06/2026 | 11.00PM

## Sheet2
Application | Tier | Has DR? | Subsidiary | App Description | Direct Customer Service | Interdependency | Schedule (H1/H2) | Date Failed Over | Failed Over? | OWNER | QUARTER