## Summary
Name of Project | TZ DR FAILOVER
Project Manager | joel.chanda/Kelvin makau
CR Number | CHG0033975
Market | TZ
Business Lead | Robert Kiboti
Down Time Required | 20*2 failover/rollback
Down Time | 40mins
Total Deployment Time

## Pre-cutover tasks
Planned Time (hh:mm)
Date | Day | Seq | Task Type | Task | Status | Verified by | Owner | Start | End | Dur.
2024-05-19 |  |  | Pre-requisite | Back of files tnsnames.ora/Database properties(with DC connections) on fincle TZ DR as below(10.1.38.65/66) | Pending |  | charles/Marion | 9:00 | 9:10 | 10 min
/apporacle/sw/app/product/12.2/client_1/network/admin$ cp tnsnames.ora tnsnames.ora_bkp_DC
back up Database properties on below paths
//etc/b2k/EQDR/PEAS/seed
/etc/b2k/EQTZDR/FINCORE/seed
/etc/b2k/EQTZDR/SIS/seed
/etc/b2k/EQTZDR/FCS/seed
//etc/b2k/EQDR/SVS/seed
|  |  |  | Create DR_bakups with DR DB Connections as below | Pending |  | charles/Marion | 9:20 | 9:50
a) Change all the TNS entries in all the 2 C++ SERVERS shown below (10.1.38.65/66)
/apporacle/sw/app/product/12.2/client_1/network/admin
b) Change all the db properties in all the servers. Put the new TNS entries. below are the paths:
//etc/b2k/EQDR/PEAS/seed
/etc/b2k/EQTZDR/FINCORE/seed
/etc/b2k/EQTZDR/SIS/seed
/etc/b2k/EQTZDR/FCS/seed
//etc/b2k/EQDR/SVS/seed

## Main Cutover Tasks
Planned Time (hh:mm)
Date | Seq | System | Task Type | Task | Status | Downtime Yes/No | Owner | Start (24hrs) | End (24hrs)
2024-05-19 | 1 |  |  | Stop all services in Both DC and DR as below |  | YES | charles/Edwin | 23:00 | 23:10 | 10
FINACLE
1.stop managed servers from weblogic console
http://tzappj2ee1.tz.ebsafrica.com:8001/console/login/LoginForm.jsp
http://tzappj2ee1dr.ebsafrica.com:8001/console/login/LoginForm.jsp
2. stop finlistval service from C++ server (DC/DR)
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/finlistval/bin
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/finlistval/bin
./stop*
3. Stop coressession service from C++ servers(DC/DR)
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/coresession/bin
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/coresession/bin
./stop*
4.stop cbc and uniser services from C++ servers(DC/DR)
/finacle/EQTZPROD/Fin10218/APP/CBC/services/cbc/bin
/finacle/EQTZDR/Fin10218/APP/CBC/services/cbc/bin
./stop*
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/uniser_55/bin
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/uniser_55/bin
./stop*
|  |  |  | Database failover |  |  | Nathan | 23:11 | 23:21 | 10
Login to DBA console 10.1.12.123
Login to DB server
Step 1: Connect to the command line
dgmgrl
connect sys/<psswd>@EQBLCDB
Step 2: Check that both the Primary and Standby databases are in sync
DGMGRL> show configuration
Step 3: Switch Over to DR:
DGMGRL> switchover to ebkstdby
Step 4: Check if the switchover is successful and the database roles have been reversed
DGMGRL> show configuration
Step 5: Switching Back to Primary Site
connect to the command line using the commands in step 1 above
Step 6: Switch back to DC
DGMGRL> switchover to eqblcdb
Step 7: Check if the switchover is successful and the database roles have been reversed using steps 4 above

## DR Cutover tasks
Planned Time (hh:mm)
Date | Date | Seq | System | Task Type | Task | Status | Downtime Yes/No | Owner | Start (24hrs) | End (24hrs)
| 2024-05-19 | 1 |  |  | Deployment of files
|  |  | Finacle |  | Login to core banking console 10.1.12.127
[5 empty] | 1. ACTUAL PROCEDURE |  |  |  | 10mins
2015-03-21 | [6 empty] | YES | Charles/Edwin | 23:11pm | 23:21pm
a) Change all the TNS entries in all the 2 C++ SERVERS shown below (10.1.38.65/66)
+
Cp bkp_dr_tnsnames.ora (done on precutover)tnsnames.ora
b) Change all the db properties in all the servers. With DR_bkps
//etc/b2k/EQDR/PEAS/seed
/etc/b2k/EQTZDR/FINCORE/seed
/etc/b2k/EQTZDR/SIS/seed
/etc/b2k/EQTZDR/FCS/seed
2015-03-22 |  |  |  |  | //etc/b2k/EQDR/SVS/seed
c) In WEBLOGIC console Change all the Data sources in all the components to reflect the new Database details
http://tzappj2ee1dr.ebsafrica.com:8001/console/login/LoginForm.jsp
DC URL
jdbc:oracle:thin:@(DESCRIPTION=(ADDRESS=(PROTOCOL=TCP)(HOST=findbtzn-scan)(PORT=1580))(CONNECT_DATA=(SERVER=DEDICATED)(SERVICE_NAME=ebgfintz.tz.ebsafrica.com)))
DR URL
jdbc:oracle:thin:@(DESCRIPTION=(ADDRESS=(PROTOCOL=TCP)(HOST=drdb02-c6-scan)(PORT=1572))(CONNECT_DATA=(SERVER=DEDICATED)(SERVICE_NAME=ebtzfidr.ebsafrica.com)))
[5 empty] | d) Restart All Services as below |  | 12 |  | 10(mins)
[5 empty] | 1. Restart managed servers from weblogic console |  |  |  | 23:22 | 23:32
http://tzappj2ee1dr.ebsafrica.com:8001/console/login/LoginForm.jsp
2. Restart finlistval service from C++ server
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/finlistval/bin
./start*
3. Restart coressession service from C++ servers
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/coresession/bin
./start*
4. Restart cbc and uniser services from C++
/finacle/EQTZDR/Fin10218/APP/CBC/services/cbc/bin
./start*
/finacle/EQTZDR/Fin10218/APP/Finacle/FC/app/services/uniser_55/bin
./start*

## RollBack Procedure
Planned Time (hh:mm)
Date | Date | Seq | Task Type | Task | Status | Downtime Yes/No | Owner | Start (24hrs) | End (24hrs) | Dur. | Comments
| 2024-05-20 | 1 |  | Redeployment of the back up files for all DC_DB property files in DR(10.1.38.65/66) |  | yes | charles/Edwin | 0:50 | 1:00 | 10(mins)
|  | 2 |  | Update DC DB connection string in weblogic managed server
http://tzappj2ee1dr.ebsafrica.com:8001/console/login/LoginForm.jsp
|  | 3 |  | Database Roll back |  | yes | Nathan | 0:50 | 1:00 | 10mins
|  | 4 |  | Start all services in DC |  | yes |  | 1:01 | 1:11 | (10mins)
1. Restart managed servers from weblogic console
http://tzappj2ee1.tz.ebsafrica.com:8001/console/login/LoginForm.jsp
start core services:
2. Restart finlistval service from C++ server
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/finlistval/bin
./start*
3. Restart coressession service from C++ servers
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/coresession/bin
./start*
4. Restart cbc and uniser services from C++
/finacle/EQTZPROD/Fin10218/APP/CBC/services/cbc/bin
./start*
/finacle/EQTZPROD/Fin10218/APP/Finacle/FC/app/services/uniser_55/bin
./start*

## Contacts
Name | DO NOT EDIT | DO NOT EDIT | Role | Telephone | Escalation | Escalation Numbers
Charles Ndirangu | 0722630697/0763630697 | Charles Ndirangu | MANAGER | 0722395534 / 0763395534 | John wamai | 763626695
Edwin Zico |  |  | Oficer | 0727992351/0763992351 | John wamai | 763626695
Flavianna masswe |  |  | IT TZ | 255757696777 | joel.chanda
Nathan njuguna |  |  | DBA | 254722980197 | fredrick.kitunga | 722325000
Amos Kimiti |  |  | System Admin | 254763247474 | antony mwai | 763869051

## Test Plan
Planned Time (hh:mm)
Day | Seq | Task | Status | Verified by | Owner | Start | End | Dur.
Regression on all services in affected service tab

## Services Affected
impacted services | Technical support team required | Department Lead
Finacle Login | Samuel Mbogori | John Wamai/Kelvin Makau
New Gen | Elizabeth
OMNI | Judynelly
OMN/BSH | Elizabeth/
EazzyBiz: Account Summary | Titus Kiptalam
EazzyBiz: Online Statement | Titus Kiptalam
EazzyBiz: FT to Mobile wallet | Titus Kiptalam
EazzyBiz: FT A2A transaction | Titus Kiptalam
EazzyBiz: Bulk Transactions | Titus Kiptalam
Johari | Timothy Karemeri
Bio: Finacle Login validation | Kim Mugambi
Bio: Query CIF | Kim Mugambi
Bio Portal | Kim Mugambi
SOA: EazzyBiz: FT A2A transaction | Charles K
MFS: FT to Equity Account | Millicent Ocha/john karanja
MFS: FT to Mobile Wallet | Millicent Ocha/john karanja
MFS: Agent Cash withdrawal | Millicent Ocha/john karanja
MFS: bill payment | Millicent Ocha/john karanja
MFS: Mini Statement | Millicent Ocha/john karanja
MGW: EazzyPay | Millicent Ocha/john karanja
MGW: Loan Payment | Millicent Ocha/john karanja
GAG: Buy Airtime to Safaricom | Millicent Ocha/john karanja
GAG: FT to Mobile Wallet | Millicent Ocha/john karanja
GAG IMT | Mathew Kinyua
Pesalink: Send money to other bank | Millicent Ocha/john karanja
Way4: Agent cash withdrawal | Judith Onyach/victor kinyanjui
Way4: Agent cash Deposit | Judith Onyach/victor kinyanjui
Way4:POS Payment | Judith Onyach/victor kinyanjui
Way4: ATM Balance Inquiry | Judith Onyach/victor kinyanjui
Way4: ATM cash withdrawal | Judith Onyach/victor kinyanjui
Efront: account Balance | Marion Kinyanjui
Efront: account Statement | Marion Kinyanjui
Diaspora Portal: Check bank Account balance | Titus Kiio
Diaspora Portal: Withdraw - paypal to Bank Account | Titus Kiio
ORS : FT to Equity Account | Mathew Kinyua
Phone Solution | Kim Mugambi